## Executive Summary
Sakshi AI Gen 3 — Master Project Plan & Execution Tracker
PROJECT OVERVIEW
Field | Details
Project Name | Sakshi AI Gen 3 — Enterprise Invoice & ERP Automation Engine
Project Lead | Rahul
Target Completion Date | 4-Week Sprint Schedule
Primary Goal | Automated AI Extraction, 7-Pillar Accounting Review, GST/TDS Compliance, and Direct Zoho Books Sync
KEY MILESTONES SCHEDULE
Milestone ID | Target Date | Deliverable Description | Owner | Status
MS-01 | End of Week 1 | AI Extraction Engine & Pydantic Validation Schemas Ready | Member 2 | Completed
MS-02 | End of Week 2 | Zoho Books Resilient Middleware & Tax/TDS Brain Fully Integrated | Member 3 | Completed
MS-03 | End of Week 3 | Frontend 7-Pillar Review Hub, Gmail Auto-Ingestion & Sticky Buckets | Member 4 / Rahul | Completed
MS-04 | End of Week 4 | 43 Enterprise Test Scenarios Execution, UAT Approval & Production Handover | All 4 Members | In Progress

## Master Task List (WBS)
Master Task List & Work Breakdown Structure (WBS)
Task ID | Module / Component | Task Description | Primary Owner | Est. Hours | Start Date | End Date | Status
WBS 1.1 | AI Vision Engine | Fine-tune Qwen3-VL 4B Vision Model for Invoice Extraction | Member 2 | 24 | Day 1 | Day 3 | Done
WBS 1.2 | AI Vision Engine | Update Notebook System Prompt for Indian TDS (194I/J/C/H/Q) & SKU Rules | Member 2 | 16 | Day 3 | Day 5 | Done
WBS 1.3 | Data Sanitization | Build Pydantic Schema (schemas/invoice.py) with PAN Slicer & Math Police | Rahul | 20 | Day 4 | Day 6 | Done
WBS 1.4 | Data Sanitization | Implement SEZ State Sanitizer, Customer GSTIN Copy-Paste Fixer, Tax Auto-Calc | Rahul | 16 | Day 6 | Day 7 | Done
WBS 2.1 | ERP Integration | Build Zoho OAuth2 Resilient Client with Token Refresh Auto-Healer | Member 3 | 20 | Day 8 | Day 10 | Done
WBS 2.2 | ERP Integration | Implement Vendor Profile Upsert (company_name, Phone, Email, GST/PAN) | Member 3 | 16 | Day 10 | Day 12 | Done
WBS 2.3 | Tax Brain | Develop resolve_tax_id() with Intrastate/Interstate & Fallback Rate Matching | Member 3 | 20 | Day 11 | Day 13 | Done
WBS 2.4 | Category Engine | Implement Semantic Keyword Matcher for Zoho Chart of Accounts | Rahul | 16 | Day 13 | Day 14 | Done
WBS 2.5 | Auto-Healer | Build Historical Invoice Date Auto-Retry Engine for TDS Effective Date Lock | Rahul | 12 | Day 14 | Day 14 | Done
WBS 3.1 | Frontend Hub | Build Next.js 7-Pillar Review Hub (page.tsx) with PDF/Data side-by-side view | Member 4 | 28 | Day 15 | Day 18 | Done
WBS 3.2 | Frontend Hub | Implement Split-Bucket Dashboard (Action Required vs Synced) with Sticky Headers | Member 4 | 20 | Day 18 | Day 20 | Done
WBS 3.3 | Gmail Ingestion | Build Gmail OAuth Ingestion (GET /google/emails & POST /google/extract) | Rahul | 16 | Day 19 | Day 21 | Done
WBS 3.4 | UI UX Fixes | Add AI TDS Prediction Warning Badge & Clear File Upload Memory State | Member 4 | 12 | Day 21 | Day 21 | Done
WBS 4.1 | QA & Compliance | Create & Execute 43 Enterprise Test Scenarios Matrix | Member 4 / All | 32 | Day 22 | Day 25 | In Progress
WBS 4.2 | Security & Deployment | Enforce Database Row Level Security (RLS) & Multi-Tenant Token Auditing | Rahul | 16 | Day 25 | Day 26 | Pending
WBS 4.3 | User Acceptance | Conduct Finance Team UAT Walkthrough & Sign-off | All 4 Members | 16 | Day 27 | Day 28 | Pending
|  |  | Total Estimated Hours: | 300

## QA Test Suite (43 Cases)
Use Cases & Enterprise Test Suite (43 QA Scenarios)
Use Case ID | Functional Area | Scenario Description | Expected Outcome | Verification Status
TC-01 | Vendor Management | Out-of-state vendor with mismatched tax bucket | Auto-detected, flagged needs_review = true, firewall blocks bad sync | Passed
TC-02 | GST Compliance | Intrastate Maharashtra to Maharashtra commercial rent | Auto-resolves CGST 9% + SGST 9% tax IDs | Passed
TC-03 | GST Compliance | Special Economic Zone (SEZ) Supplier invoice | Applies SEZ 0% IGST override regardless of physical vendor state | Passed
TC-04 | TDS Engine | IT / DevOps Technical Consulting Invoice | Auto-predicts Section 194J (2% or 10%) | Passed
TC-05 | TDS Engine | Commercial Lease Rent Invoice | Auto-predicts Section 194I (10%) | Passed
TC-06 | TDS Engine | Invoice date in past year (2024) vs current TDS tax date | Auto-healer retries with active date 2026-08-29 | Passed
TC-07 | Category Engine | IT Hardware purchase (27-inch 4K LED Monitors) | Maps semantically to "Computer Equipment" instead of defaulting to "Lodging" | Passed
TC-08 | Vendor Profile | Vendor update with new Bank A/C & IFSC | Vendor module in Zoho updated with company_name, phone, email, bank notes | Passed
TC-09 | Security & Control | Math discrepancy > ₹2.00 (Line items vs Subtotal) | Flags needs_review = true, turns fields red, disables Sync button | Passed
TC-10 | System Resilience | Sync fails or user clicks "Save for Later" | Retains invoice safely in Action Required (Drafts) bucket for later resumption | Passed
TC-11 | UX Optimization | Uploading file & switching views | Clears file memory state so old upload doesn't linger in dropzone | Passed
TC-12 | UX Optimization | Scrolling through long draft lists | Sticky headers keep "Action Required" and "Synced to Zoho" pinned at top | Passed
TC-13 to TC-43 | Edge Cases | Foreign Currency (FX), Reverse Charge (RCM), Duplicate Idempotency Locks, Non-Invoice Rejection, etc. | Handled gracefully by Pydantic validation & Zoho middleware | Passed

## Timeline & Weekly Schedule
Weekly Timeline & Phase Schedule
PHASE / TASK BREAKDOWN WITH DATES
Phase | Task | Start Date | Duration (days) | Status
Phase 1: AI & Schemas | Qwen-VLM Prompt & SKUs | 2026-08-01 | 5 | Done
Phase 1: AI & Schemas | Pydantic Schema & Math Police | 2026-08-04 | 4 | Done
Phase 2: ERP Integration | Zoho OAuth & Vendor Upsert | 2026-08-08 | 5 | Done
Phase 2: ERP Integration | Tax & TDS Brain Engine | 2026-08-12 | 5 | Done
Phase 2: ERP Integration | Historical Date Auto-Healer | 2026-08-16 | 2 | Done
Phase 3: Frontend Hub | 7-Pillar Review UI & Sticky Grid | 2026-08-18 | 5 | Done
Phase 3: Frontend Hub | Gmail Auto-Ingestion Pipeline | 2026-08-22 | 4 | Done
Phase 4: QA & Launch | 43 Scenario Test Execution | 2026-08-26 | 4 | In Progress
Phase 4: QA & Launch | UAT & Production Sign-off | 2026-08-30 | 3 | Pending
WEEKLY SUMMARY
Sprint Week | Key Focus Areas | Assigned Members | Output Deliverable
Week 1 (Days 1-7) | AI Vision Extraction, System Prompts, Pydantic Schema Validation | Rahul, Member 2 | Tested Colab VLM Server & schemas/invoice.py
Week 2 (Days 8-14) | Zoho Books OAuth2, Vendor Upsert, Tax Brain & Semantic Category Matcher | Rahul, Member 3 | Complete Backend API Services & Auto-Healer
Week 3 (Days 15-21) | Next.js Frontend 7-Pillar UI, Gmail API Ingestion, Sticky Buckets | Member 4, Rahul | Interactive Review Hub & Dashboard
Week 4 (Days 22-28) | End-to-End QA Testing Suite, Security RLS, Finance Team UAT | All 4 Members | Final Production Sign-off & Release

## RACI Matrix
Resource Responsibility Matrix (RACI)
RACI Legend: R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Task / Module | Rahul (Lead/Architect) | Member 2 (AI Engineer) | Member 3 (Backend/ERP) | Member 4 (Frontend/QA)
Overall Architecture & System Design | A / R | C | C | C
Qwen-VLM Prompt & Notebook Engineering | A | R | I | I
Pydantic Schema & Math Police Validation | A / R | C | C | I
Zoho OAuth2 & Resilient Middleware | A | I | R | I
Tax Brain & Semantic Category Matcher | A / R | I | C | I
Frontend 7-Pillar Review Hub & UI | A | I | I | R
Gmail OAuth & Attachment Ingestion | A / R | I | C | C
43 Enterprise Test Cases Execution | A | C | C | R
Security (RLS) & Production Deployment | A / R | I | C | I