## Executive Summary
Sakshi AI Gen 3 — Team Contribution Tracker & Master Project Status
PROJECT OVERVIEW
Field | Details
Project Name | Sakshi AI Gen 3 — Enterprise Multi-Tenant Invoice, Tax & GL Automation Engine
Architecture & Core Engineering | Rahul (Primary Lead) & Abhishek (Core Engineering Co-Lead)
Compliance & ERP Integration Lead | Raju (TDS Withholding Brain, GST Rules & Zoho Books OAuth2/Export)
Channel Ingestion & Staging Lead | Neeraj (IMAP Multi-Server Email Ingestion, PDF Renderer & Inbox Pipeline)
Current Project Health | 81.8% Core Functional Readiness ¦ 111 Passed Automated Tests ¦ Live Staging Active
Primary Business Deliverables | AI Extraction, 7-Pillar HITL Review, Deterministic GST/ITC/TDS, Balanced GL & Direct Zoho Sync
Current Active Focus | Resolution of Unbalanced Extraction Edge Cases, Full Multi-State E2E UAT, Production Deployment
TEAM FUNCTIONAL OWNERSHIP & WORK ALLOCATION
Team Member | Primary Functional Ownership | Secondary / Support Areas | Status
Rahul | Backend Core Architecture, DB Models, Duplicate Detection, Financial Validation Engine, Security/Auth RBAC | Frontend Invoices Hub, HITL Review UI, Automated Test Suite | Active
Abhishek | Frontend UI Architecture, 7-Pillar Review Workspace, GL Journal Inspector, Accounting Period & Multi-Tenant Controls | Backend API Routers, Invoice Pipeline, Storage Service, E2E Testing | Active
Raju | TDS Withholding Engine (Sec 194C/J/I/Q), Zoho Books OAuth2 Client, Master Data Sync & GL Bill Export Service | GST & ITC Compliance Rules, Accounting Classification Validation | Active
Neeraj | IMAP Multi-Server Email Ingestion, Background Polling Service, PDF Multi-Page Renderer, Staged Inbox Workspace | Settings Configuration UI, Duplicate Attachment Filtering | Active
KEY MILESTONES SCHEDULE & ACTUAL STATUS
Milestone ID | Target Schedule | Deliverable Description | Primary Owner | Actual Status
MS-01 | Phase 1 | Storage, Multi-Tenant Database, Schema Validation & Qwen-VL Integration | Rahul (Primary) / Abhishek (Support) | Completed
MS-02 | Phase 2 | Deterministic GST, ITC, TDS & Stage 5 Financial Validation Engines | Raju (TDS) / Rahul (Validation) / Abhishek (GST/ITC) | Completed
MS-03 | Phase 3 | Double-Entry Journal Generator, Relational GL Ledger & HITL Approval Lock | Abhishek (Primary) / Rahul (Support) | Completed
MS-04 | Phase 3 | Resilient Zoho Books OAuth2 Middleware, Master Data Sync & Bill Export | Raju | Completed
MS-05 | Phase 3 | IMAP Email Auto-Ingestion Engine, PDF Page Renderer & Staged Inbox UI | Neeraj | Completed
MS-06 | Phase 4 | Frontend 7-Pillar Review Hub, GL Inspector & Integrations Management | Abhishek (Primary) / Rahul (Support) | Completed
MS-07 | Phase 4 | Comprehensive Automated Test Suite (111 Backend Unit & Integration Tests) | Rahul / Abhishek / Raju / Neeraj | Completed
MS-08 | Phase 5 | End-to-End Enterprise UAT Approval, Production Hardening & Cloud Rollout | Rahul / Abhishek / Raju / Neeraj | In Progress
CURRENT PROJECT EXECUTION METRICS
Metric Category | Total Inventory | Completed / Verified | In Progress / Partial | Pending / Next Up
Master WBS Tasks (Total Inventory: 44 Tasks) | 44 Tasks | 36 Done (81.8%) | 5 In Progress / Partial (11.4%) | 3 Pending (6.8%)
QA Automated & Integration Tests | 113 Test Cases | 111 Passed (98.2%) | 2 Needs PyMuPDF / Async Fix | 0 Failed
Enterprise Functional Use Cases | 43 Scenarios | 34 Verified / Active | 5 In Progress / Verification | 4 Future / Edge Scenarios

## Master Task List (WBS)
Master Task List & Work Breakdown Structure (WBS) — Actual Repository Implementation
Task ID | Module / Component | Task Description | Primary Owner | Est. Hours | Start Date | End Date | Status
WBS 1.1 | Invoice Ingestion & Storage | Multi-tenant file upload API with SHA-256 deduplication and local disk storage backend | Rahul (Primary) / Abhishek (Support) | 20 | 2026-08-01 | 2026-08-03 | Done
WBS 1.2 | Duplicate Detection | Hash-based and fuzzy vendor/invoice_no/date duplicate prevention and staging promotion | Abhishek (Primary) / Rahul (Support) | 16 | 2026-08-03 | 2026-08-05 | Done
WBS 1.3 | IMAP Email Ingestion Service | Background email polling engine with SSL/TLS, multi-server support, and attachment extraction | Neeraj | 24 | 2026-08-10 | 2026-08-14 | Done
WBS 1.4 | Inbox Staging API | Staged document lifecycle management, duplicate filtering, and batch manual promotion to processing | Neeraj | 18 | 2026-08-14 | 2026-08-18 | Done
WBS 1.5 | PDF Multi-Page Renderer | PyMuPDF-based multi-page PDF document inspection and base64 thumbnail rendering service | Neeraj | 16 | 2026-08-18 | 2026-08-21 | Done
WBS 1.6 | IMAP Configuration & Settings API | Secure storage of user IMAP credentials with encryption, connection test endpoint, and disconnect handler | Neeraj | 14 | 2026-08-21 | 2026-08-24 | Done
WBS 2.1 | Qwen-VL Vision Client | FastAPI integration with Qwen3-VL Colab GPU server for Indian B2B invoice OCR & key-value parsing | Rahul (Primary) / Abhishek (Support) | 24 | 2026-08-02 | 2026-08-06 | Done
WBS 2.2 | Pydantic Extraction Schemas | Comprehensive validation schemas for invoice headers, line items, bank details, and PAN/GSTIN slicers | Rahul (Primary) / Abhishek (Support) | 18 | 2026-08-05 | 2026-08-08 | Done
WBS 2.3 | Dual-State JSONB Architecture | Raw vs Current VLM and Accounting outputs preservation for full HITL audit trail and rollback | Abhishek (Primary) / Rahul (Support) | 16 | 2026-08-08 | 2026-08-11 | Done
WBS 2.4 | Invoice Data Normalization | Dynamic numeric parser, Indian date normalizer, and multi-currency symbol cleaner | Rahul (Primary) / Abhishek (Support) | 14 | 2026-08-10 | 2026-08-12 | Done
WBS 2.5 | Non-Invoice Document Detection | AI rejection rules for non-invoices (statements, receipts, IDs, delivery challans) | Abhishek (Primary) / Rahul (Support) | 12 | 2026-08-12 | 2026-08-14 | Done
WBS 3.1 | COA Classification Engine | Qwen3-4B semantic keyword & rule-based Chart of Accounts categorization for line items | Abhishek (Primary) / Rahul (Support) | 20 | 2026-08-12 | 2026-08-16 | Done
WBS 3.2 | TDS Withholding Engine | Deterministic Section 194C, 194J (2%/10%), 194I (Rent), 194Q & 206AB threshold calculation | Raju | 24 | 2026-08-14 | 2026-08-18 | Done
WBS 3.3 | Vendor PAN & TDS Rules Slicer | PAN 4th character entity detector (Company vs Individual) and PAN non-furnishing 20% penalty rules | Raju | 16 | 2026-08-18 | 2026-08-20 | Done
WBS 3.4 | Cost Centre & Dimensions Engine | Tracking cost centers, project codes, and departments across line items | Abhishek (Primary) / Rahul (Support) | 14 | 2026-08-20 | 2026-08-22 | Partially Completed
WBS 4.1 | Deterministic GST Engine | Intra-State vs Inter-State supply type determination, state code resolver, and tax rate matcher | Abhishek (Primary) / Rahul (Support) | 20 | 2026-08-15 | 2026-08-19 | Done
WBS 4.2 | SEZ & RCM Tax Logic | Special Economic Zone 0% IGST overrides and Reverse Charge Mechanism tax liability handler | Rahul (Primary) / Abhishek (Support) | 16 | 2026-08-19 | 2026-08-21 | Done
WBS 4.3 | ITC Eligibility Engine | Section 16 eligibility criteria evaluation and Section 17(5) blocked credit classifier | Abhishek (Primary) / Rahul (Support) | 18 | 2026-08-20 | 2026-08-23 | Done
WBS 5.1 | Financial Validation Engine | Independent mathematical cross-reconciliation (lines, subtotal, tax breakdown, grand total) | Rahul (Primary) / Abhishek (Support) | 22 | 2026-08-21 | 2026-08-24 | Done
WBS 5.2 | Reconciliation Anomaly Detector | Line-item math mismatch detection, rounding difference handler, and discrepancy warnings | Rahul (Primary) / Abhishek (Support) | 16 | 2026-08-23 | 2026-08-25 | Done
WBS 5.3 | Double-Entry Journal Generator | Deterministic balanced debits (expenses/assets/input tax) vs credits (AP/TDS) preview generator | Abhishek (Primary) / Rahul (Support) | 24 | 2026-08-22 | 2026-08-25 | Done
WBS 5.4 | Relational GL Database Sync | Idempotent persistence to relational journal_entries and journal_lines tables | Abhishek (Primary) / Rahul (Support) | 18 | 2026-08-24 | 2026-08-26 | Done
WBS 5.5 | Authoritative Accounting Validation | Mandatory Finance approval verification on COA lines and zero-fallback strict journal lock | Rahul (Primary) / Abhishek (Support) | 16 | 2026-08-25 | 2026-08-27 | Done
WBS 6.1 | Invoice Review API | CRUD operations for draft edits, line-item account overrides, and draft journal preview | Abhishek (Primary) / Rahul (Support) | 18 | 2026-08-23 | 2026-08-26 | Done
WBS 6.2 | Strict Approval & Lock Workflow | Atomic invoice approval state machine, balanced journal gatekeeper, and tamper-proof lock | Rahul (Primary) / Abhishek (Support) | 18 | 2026-08-26 | 2026-08-28 | Done
WBS 6.3 | Rejection & Reason Logging | Invoice rejection workflow with mandatory audit trail reason logging | Abhishek (Primary) / Rahul (Support) | 12 | 2026-08-26 | 2026-08-28 | Done
WBS 6.4 | Audit Trail Service | Detailed event logging for all user interactions, state mutations, and export attempts | Rahul (Primary) / Abhishek (Support) | 14 | 2026-08-26 | 2026-08-28 | Done
WBS 6.5 | Accounting Period Controls | Fiscal calendar validation, closed period locking, and back-dated posting controls | Rahul (Primary) / Abhishek (Support) | 16 | 2026-08-28 | 2026-08-30 | Partially Completed
WBS 7.1 | Zoho OAuth2 Client | Resilient OAuth2 token lifecycle management with automated refresh and secure encryption | Raju | 24 | 2026-08-16 | 2026-08-20 | Done
WBS 7.2 | Zoho Master Data Sync | Synchronizing Chart of Accounts, Tax Rates, Vendors, Payment Terms, and Cost Centers | Raju | 20 | 2026-08-20 | 2026-08-24 | Done
WBS 7.3 | Zoho Vendor Auto-Upsert | Auto-creation and update of vendor contacts in Zoho with GSTIN, PAN, and bank details | Raju | 18 | 2026-08-22 | 2026-08-25 | Done
WBS 7.4 | Zoho Bill Export Service | Direct export of approved invoices as Zoho Bills with line accounts, tax mappings, and TDS credits | Raju | 22 | 2026-08-24 | 2026-08-28 | Done
WBS 7.5 | Zoho Error Handling & Auto-Healer | Resilient error recovery for rate limits, effective date lock retries, and duplicate bill numbers | Raju | 16 | 2026-08-26 | 2026-08-29 | Done
WBS 7.6 | Credit / Debit Notes Support | Handling vendor credit notes and debit adjustments in Zoho sync workflow | Raju | 16 | 2026-08-28 | 2026-08-31 | In Progress
WBS 8.1 | Next.js App Architecture | AppShell navigation, responsive layout, sidebar routes, and authenticated state handling | Abhishek (Primary) / Rahul (Support) | 20 | 2026-08-18 | 2026-08-22 | Done
WBS 8.2 | 7-Pillar Review Workspace | Interactive split-view review page (PDF/Image viewer + 7 validation and accounting pillars) | Abhishek (Primary) / Rahul (Support) | 28 | 2026-08-22 | 2026-08-26 | Done
WBS 8.3 | Journal & GL Inspector UI | Live double-entry preview card showing Debits vs Credits, balance status badge, and diffs | Abhishek (Primary) / Rahul (Support) | 16 | 2026-08-24 | 2026-08-27 | Done
WBS 8.4 | Finance Invoices Workspace | Categorized invoice tabs (Drafts, Approved, Exported, Failed) with sticky headers and search | Abhishek (Primary) / Rahul (Support) | 18 | 2026-08-25 | 2026-08-28 | Done
WBS 8.5 | Staged Email Inbox UI | Document staging workspace, polling trigger button, email metadata viewer, and promotion modal | Neeraj / Abhishek | 16 | 2026-08-26 | 2026-08-29 | Done
WBS 8.6 | Integrations Management Hub | Zoho Books connection status, master data browser, and IMAP configuration drawer | Abhishek (Primary) / Raju (Support) | 16 | 2026-08-26 | 2026-08-29 | Done
WBS 9.1 | Authentication & RBAC | JWT bearer authentication, role-based access control (ADMIN, FINANCE, VIEWER), and login UI | Rahul (Primary) / Abhishek (Support) | 18 | 2026-08-25 | 2026-08-28 | Done
WBS 9.2 | Multi-Tenancy & Data Isolation | Strict tenant_id enforcement across all database queries, migrations, and storage paths | Rahul (Primary) / Abhishek (Support) | 16 | 2026-08-26 | 2026-08-29 | Done
WBS 9.3 | Automated Regression Test Suite | 113 unit, integration, and security test scenarios covering Stages 1 to 6 | Rahul (Primary) / Abhishek (Support) | 24 | 2026-08-27 | 2026-08-30 | Done
WBS 9.4 | Vendor Real-time Validation API | Live GSTIN / PAN validation against government portals / external APIs | Rahul (Primary) / Raju (Support) | 16 | 2026-08-29 | 2026-09-02 | In Progress
WBS 9.5 | Production Deployment & Cloud Setup | Docker containerization, Supabase DB pooling, environment configs, and SSL reverse proxy | Rahul (Primary) / Abhishek (Support) | 20 | 2026-08-29 | 2026-09-03 | In Progress
WBS 9.6 | End-to-End Enterprise UAT Sign-off | Finance team walkthrough, edge-case reconciliation resolution, and user sign-off | All Team Members | 20 | 2026-08-30 | 2026-09-04 | Needs Verification
Total Estimated Hours:

## QA Test Suite (43 Cases)
QA Test Suite & Functional Verification Matrix (43 Enterprise Scenarios)
Use Case ID | Functional Area | Scenario Description | Responsible Owner | Expected System Behavior | Verification Status
TC-01 | Vendor Management | Out-of-state vendor with mismatched tax bucket | Rahul (Primary) / Abhishek (Support) | Auto-detected by GST engine, flagged MISMATCH, blocks premature sync | Passed
TC-02 | GST Compliance | Intrastate Maharashtra to Maharashtra commercial supply | Abhishek (Primary) / Rahul (Support) | Auto-resolves CGST 9% + SGST 9% tax accounts deterministically | Passed
TC-03 | GST Compliance | Special Economic Zone (SEZ) Supplier invoice | Rahul (Primary) / Abhishek (Support) | Applies SEZ 0% IGST override regardless of physical vendor state | Passed
TC-04 | TDS Engine | IT / DevOps Technical Consulting Invoice | Raju | Auto-predicts Section 194J Professional Fees (2% or 10%) | Passed
TC-05 | TDS Engine | Commercial Lease / Rent Invoice | Raju | Auto-predicts Section 194I Land/Building Rent (10%) | Passed
TC-06 | TDS Engine | Contractor Works / Maintenance Services Invoice | Raju | Auto-predicts Section 194C Contractor Withholding (1% / 2%) | Passed
TC-07 | TDS Engine | Vendor PAN non-furnishing / invalid PAN detection | Raju | Triggers higher deduction rate penalty (20%) under Section 206AA | Passed
TC-08 | TDS Engine | Invoice date in past year vs active TDS financial lock | Raju | Auto-healer retries with active effective tax date in current fiscal cycle | Passed
TC-09 | COA Category Engine | IT Hardware purchase (27-inch 4K LED Monitors) | Abhishek (Primary) / Rahul (Support) | Maps semantically to Computer Equipment asset/expense account | Passed
TC-10 | Vendor Profile | Vendor update with new Bank Account & IFSC details | Raju | Zoho vendor contact upserted with company name, email, and bank notes | Passed
TC-11 | Financial Validation | Math discrepancy > ₹1.00 (Line items taxable sum vs Subtotal) | Rahul (Primary) / Abhishek (Support) | Flags overall_status = MISMATCH, records diff warnings, marks review needed | Passed
TC-12 | Financial Validation | Multi-line item arithmetic check (Qty × Unit Price vs Total) | Rahul (Primary) / Abhishek (Support) | Validates per-line arithmetic independently and isolates faulty line items | Passed
TC-13 | Financial Validation | Header tax total vs sum of CGST + SGST + IGST components | Rahul (Primary) / Abhishek (Support) | Confirms exact penny equality between tax header and component sums | Passed
TC-14 | Journal Generator | Double-entry balance check (Total Debits == Total Credits) | Abhishek (Primary) / Rahul (Support) | Enforces Debits == Credits within ₹1.00 tolerance or marks UNBALANCED | Passed
TC-15 | Journal Generator | Ineligible input tax under Section 17(5) accounting | Abhishek (Primary) / Raju (Support) | Routes ineligible GST debits to Ineligible Input Tax Expense account | Passed
TC-16 | Journal Generator | TDS deduction impact on Accounts Payable credit | Abhishek (Primary) / Raju (Support) | Calculates Vendor AP Credit as Gross Total minus Withheld TDS | Passed
TC-17 | Journal Generator | Round-off penny difference handling (<= ₹1.00) | Abhishek (Primary) / Rahul (Support) | Automatically injects balancing debit/credit round-off adjustment line | Passed
TC-18 | HITL Approval | Approve invoice with complete Finance-approved COA lines | Rahul (Primary) / Abhishek (Support) | Generates authoritative journal, locks invoice, stamps approved_by and approved_at | Passed
TC-19 | HITL Approval | Attempt approval on unapproved AI-suggested COA line | Rahul (Primary) / Abhishek (Support) | Throws HTTP 400 rejecting approval until Finance explicitly confirms account | Passed
TC-20 | HITL Approval | Attempt approval on unbalanced journal entry | Rahul (Primary) / Abhishek (Support) | Throws HTTP 400 blocking approval with exact Debit/Credit difference details | Passed
TC-21 | HITL Rejection | Finance manager rejects invoice with mandatory reason note | Abhishek (Primary) / Rahul (Support) | Sets status to REJECTED, unlocks edits, and logs audit event | Passed
TC-22 | Audit Trail | Full lifecycle audit tracking from upload to Zoho sync | Rahul (Primary) / Abhishek (Support) | Records timestamped audit log entries with user email, action, and IP context | Passed
TC-23 | Duplicate Detection | Exact duplicate invoice file upload (same SHA-256 hash) | Rahul (Primary) / Abhishek (Support) | Rejects upload with HTTP 409 Conflict and existing invoice link | Passed
TC-24 | Duplicate Detection | Re-uploading failed / staged document file | Abhishek (Primary) / Rahul (Support) | Promotes existing staged record to processing without duplicating records | Passed
TC-25 | Multi-Tenancy | Tenant A accessing Tenant B invoice via direct UUID | Rahul (Primary) / Abhishek (Support) | Returns HTTP 404/403 strictly isolating tenant data across all queries | Passed
TC-26 | Auth & RBAC | Viewer role attempting invoice approval or COA override | Rahul (Primary) / Abhishek (Support) | Returns HTTP 403 Forbidden enforcing ADMIN/FINANCE role requirements | Passed
TC-27 | IMAP Email Ingestion | Polling Gmail mailbox with Google App Password over SSL | Neeraj | Fetches UNSEEN emails with PDF/image attachments and stages in inbox | Passed
TC-28 | IMAP Email Ingestion | Catching IMAP authentication failures with clear user guidance | Neeraj | Returns actionable error instructing Google 2FA & App Password configuration | Passed
TC-29 | Inbox Staging | Promoting staged email attachment to main invoice review pipeline | Neeraj | Creates new invoice record, triggers VLM extraction, updates staged status | Passed
TC-30 | PDF Page Rendering | Multi-page PDF invoice preview generation via PyMuPDF | Neeraj | Renders all pages as high-res images for side-by-side review workspace | Passed
TC-31 | Zoho OAuth2 | Initial OAuth2 handshake and authorization code exchange | Raju | Exchanges authorization code for access/refresh tokens and encrypts in DB | Passed
TC-32 | Zoho OAuth2 | Access token expiration during background operations | Raju | Auto-refreshes access token transparently using encrypted refresh token | Passed
TC-33 | Zoho Master Data | Fetching Zoho Chart of Accounts, Taxes, and Payment Terms | Raju | Synchronizes remote Zoho master data into local cache with summary counts | Passed
TC-34 | Zoho Bill Export | Exporting approved invoice with valid accounts and tax IDs | Raju | Creates vendor bill in Zoho Books and updates zoho_bill_id on invoice | Passed
TC-35 | Zoho Bill Export | Attempting export of unapproved or draft invoice | Raju | Blocks export with HTTP 400 requiring invoice approval first | Passed
TC-36 | Zoho Resilience | Zoho API rate limit (429) or transient network error handling | Raju | Retries with exponential backoff and marks EXPORT_FAILED with reason if exhausted | Passed
TC-37 | UI Responsiveness | Side-by-side PDF viewer and 7-pillar validation cards | Abhishek (Primary) / Rahul (Support) | Smooth document zoom/pan alongside responsive data editing forms | Passed
TC-38 | UI Resilience | Preserving edited form fields across browser tab switching | Abhishek (Primary) / Rahul (Support) | Maintains local review state and provides explicit Save Draft action | Passed
TC-39 | Credit Notes Support | Handling vendor credit notes / refund adjustments | Raju | Maps negative line items and credit note payload structure to Zoho ERP | In Progress
TC-40 | Live Vendor GSTIN API | Real-time taxpayer verification against GST portal | Rahul (Primary) / Raju (Support) | Queries government API to verify active registration status and legal name | In Progress
TC-41 | Closed Accounting Period | Posting invoice dated in locked prior financial period | Rahul (Primary) / Abhishek (Support) | Enforces closed period lock and suggests adjustment in open fiscal period | Partially Completed
TC-42 | Foreign Currency (FX) | Multi-currency invoice with exchange rate conversion to INR | Rahul (Primary) / Abhishek (Support) | Extracts currency code and converts base amounts to INR for GL journal | In Progress
TC-43 | End-to-End Enterprise UAT | Full multi-vendor batch invoice processing and audit sign-off | All Team Members | Finance user acceptance testing across complete 7-pillar lifecycle | Needs Verification

## Timeline & Weekly Schedule
Project Timeline & Phase Execution Schedule — Actual Repository Progress
PHASE & SPRINT EXECUTION BREAKDOWN
Phase / Sprint | Core Task Deliverables | Start Date | End Date | Actual Status
Phase 1: Architecture & Ingestion | Multi-tenant DB schema, storage backend, hash deduplication, Qwen-VL integration | 2026-08-01 | 2026-08-08 | Done
Phase 2: Compliance Engines | Deterministic GST, ITC Section 17(5), TDS Withholding (194C/J/I/Q) engines | 2026-08-08 | 2026-08-16 | Done
Phase 3: Financial Validation & GL | Stage 5 math reconciler, Stage 6 double-entry journal generator, relational GL sync | 2026-08-16 | 2026-08-24 | Done
Phase 4: Integrations & Review UI | Zoho Books OAuth2 & bill export, IMAP email ingestion, 7-pillar review hub | 2026-08-20 | 2026-08-28 | Done
Phase 5: Automated Testing & Security | 113 automated unit/integration tests, RBAC security, multi-tenant isolation | 2026-08-25 | 2026-08-30 | Done
Phase 6: UAT & Production Launch | End-to-end enterprise UAT walkthrough, edge-case tuning, production deployment | 2026-08-30 | 2026-09-04 | In Progress
WEEKLY TEAM CONTRIBUTION & SPRINT SUMMARY
Sprint Week | Key Focus Areas | Primary Contributors | Key Deliverables & Milestones
Week 1 (Aug 01 - Aug 07) | Backend Foundations, DB Schemas, Storage, Dual-State JSONB, Qwen-VL Parsing | Rahul, Abhishek | Operational backend API, invoice upload pipeline, Pydantic schemas
Week 2 (Aug 08 - Aug 15) | GST Engine, ITC Classifier, TDS Tax Brain, Semantic COA Categorization | Raju, Rahul, Abhishek | Deterministic tax rules, PAN entity slicer, Section 194C/J/I rules
Week 3 (Aug 16 - Aug 23) | Financial Validation, Balanced GL Generator, Zoho OAuth2, IMAP Email Ingestion | Rahul, Abhishek, Raju, Neeraj | Stage 5 math reconciler, Stage 6 double entry journal, Zoho client, IMAP service
Week 4 (Aug 24 - Aug 30) | 7-Pillar Review Hub UI, Staged Inbox Workspace, GL Inspector, Zoho Bill Export | Abhishek, Rahul, Raju, Neeraj | Next.js review workspace, Zoho bill sync, 111 passed automated tests
Week 5 (Aug 31 - Sep 06) | Enterprise UAT Execution, Live Edge-Case Fixes, Production Cloud Deployment | All Team Members | Final UAT approval, production readiness, and live customer handover

## RACI Matrix
Resource Responsibility Matrix (RACI) — Real Team Structure
RACI Legend: R = Responsible (Did the Work) ¦ A = Accountable (Approver/Owner) ¦ C = Consulted ¦ I = Informed
Functional Module / Workstream | Rahul (Backend / Arch Lead) | Abhishek (Frontend / Core Co-Lead) | Raju (TDS / Zoho ERP Lead) | Neeraj (Email / IMAP Lead)
Overall System Architecture & Multi-Tenant Database | A / R | C / R | C | I
Invoice Ingestion, File Storage & Hash Deduplication | A / R | C | I | I
IMAP Email Auto-Ingestion & Inbox Staging Service | I | C | I | A / R
PDF Multi-Page Renderer & Document Previews | I | C | I | A / R
Qwen3-VL & Qwen3-4B AI Model Integrations & Schemas | A / R | C / R | I | I
Deterministic GST Engine & State Supply Type Rules | C | A / R | C | I
ITC Eligibility & Section 17(5) Blocked Credit Engine | C | A / R | C | I
TDS Withholding Engine (Sections 194C, 194J, 194I, 194Q) | I | C | A / R | I
Vendor PAN Validation & Entity Slicing (206AA) | I | C | A / R | I
Stage 5 Financial Validation & Mathematical Cross-Reconciliation | A / R | C | I | I
Stage 6 Double-Entry Journal Generator & GL Tables Sync | C | A / R | C | I
HITL Review API, Authoritative Approval & Rejection Lock | A / R | C / R | I | I
Audit Trail Logging & Event Capture Service | A / R | C | I | I
Zoho Books OAuth2 Resilient Client & Auto-Healer | I | I | A / R | I
Zoho Master Data Sync (COA, Taxes, Vendors, Terms) | I | I | A / R | I
Zoho Bill Creation & Multi-Account GL Export Engine | I | C | A / R | I
Next.js Frontend Architecture & AppShell Navigation | C | A / R | I | I
7-Pillar Review Hub UI & Split-Screen Document Viewer | C | A / R | I | I
GL Double-Entry Inspector UI & Real-Time Balance Badge | C | A / R | I | I
Integrations Hub (Zoho Status & IMAP Settings Drawer) | I | A / R | C | C
Security (JWT Auth, RBAC Roles, Tenant Isolation) | A / R | C | I | I
Automated Testing Suite (Unit, Integration, Security) | A / R | C / R | C | C
Finance Team UAT Walkthrough & Production Deployment | A / R | A / R | A / R | A / R